## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a data engineer, I want to collect and preprocess transaction data so that it can be used for model training. | MUST HAVE | Dataset availability | Backend Team | 3- Completed
Sprint 2 | Sprint 2 | US002 | As a data scientist, I want to train an ML model that predicts fraudulent transactions using historical data. | MUST HAVE | Cleaned data | Backend Team | 3- Completed
Sprint 3 | Sprint 3 | US003 | As an AI developer, I want to integrate an LLM to provide human-readable explanations for fraud predictions. | SHOULD HAVE | Trained model | Backend Team | 3- Completed
Sprint 4 | Sprint 4 | US004 | As a frontend developer, I want to create an interactive dashboard that displays transaction risk results and performance metrics. | MUST HAVE | APIs ready | Frontend Team | 3- Completed
Sprint 4 | Sprint 4 | US005 | As a DevOps engineer, I want to deploy and integrate the entire system in a test environment for demonstration. | COULD HAVE | Backend & frontend integration | Both Teams | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US001 | T1 | Collect transaction dataset and verify structure | 2025-11-12 | 2025-11-18 | Backend1 | Data Collection | 3- Completed | 6 | bar: Day 1 to Day 2
US001 | T2 | Clean missing values and normalize features | 2025-11-18 | 2025-11-25 | Backend2 | Data Cleaning | 3- Completed | 10 | bar: Day 2 to Day 4
US002 | T3 | Train ML model (Random Forest) for fraud prediction | 2025-11-28 | 2025-12-09 | Backend3 | Model Training | 3- Completed | 12 | bar: Day 3 to Day 6
US003 | T4 | Integrate LLM to generate prediction explanations | 2025-12-13 | 2025-12-23 | Backend4 | AI Integration | 3- Completed | 8 | bar: Day 4 to Day 6
US004 | T5 | Create frontend dashboard for fraud prediction visualization | 2025-12-25 | 2026-01-01 | Frontend1 | UI Development | 3- Completed | 10 | bar: Day 5 to Day 8
US005 | T6 | Deploy backend and frontend to test environment | 2026-01-02 | 2026-01-05 | Both Teams | Deployment | 3- Completed | 8 | bar: Day 6 to Day 9

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 2 | Day 3 | ML model taking too long to train due to large dataset | Reduced features and applied stratified sampling
Sprint 2 | Day 4 | API returning 500 error during prediction | Debugged endpoint, fixed missing JSON key
Sprint 3 | Day 2 | LLM responses too long and inconsistent | Applied temperature control and prompt optimization
Sprint 4 | Day 1 | Frontend not fetching data due to CORS issue | Enabled CORS in Flask backend

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-11-13 | 2025-11-24 | Backend Team | Document preprocessing steps clearly | Rushing into training without validation | Collaborating during data cleaning | Created shared preprocessing document
2 | 2 | 2025-11-26 | 2025-12-11 | Backend Team | Use version control for model files | Using large data without sampling | Testing each version before training | Implemented model versioning
3 | 3 | 2025-12-12 | 2025-12-26 | AI Team | Write prompts clearly for LLM | Using unstructured prompts | Evaluating prompt output for accuracy | Finalized best-performing prompts
4 | 4 | 2025-12-29 | 2026-01-12 | Frontend + Backend | Prepare documentation parallelly | Waiting till the end to test integration | Regular cross-team syncs | Weekly integration meetings scheduled